## Activities
task_id | task_code | task_name | wbs_id | wbs_name | status | planned_start | planned_finish | actual_start | actual_finish | original_duration | remaining_duration | phys_complete_pct | zone | planned_pct | variance_pct | weight | _tc
TASK-0001 | Z01-EXC-001 | Zone 01 - Excavation - Activity 1 | WBS-0003 | Zone 01 - Excavation | Completed | 2024-10-01 | 2024-11-05 19:12 | 2024-09-29 10:41 | 2024-11-07 05:58 | 35 | 0 | 100 | Zone 01 | 100 | 0 | 0.00038611 | 11820.9
TASK-0002 | Z01-EXC-002 | Zone 01 - Excavation - Activity 2 | WBS-0003 | Zone 01 - Excavation | Completed | 2024-11-05 19:12 | 2024-12-11 14:24 | 2024-11-04 16:37 | 2024-12-13 00:27 | 35 | 0 | 100 | Zone 01 | 100 | 0 | 0.00019864 | 6081.6
TASK-0003 | Z01-EXC-003 | Zone 01 - Excavation - Activity 3 | WBS-0003 | Zone 01 - Excavation | Completed | 2024-12-11 14:24 | 2025-01-16 09:36 | 2024-12-09 22:44 | 2025-01-15 22:21 | 35 | 0 | 100 | Zone 01 | 100 | 0 | 0.00043603 | 13349.35
TASK-0004 | Z01-PIP-001 | Zone 01 - Pipe Laying - Activity 1 | WBS-0004 | Zone 01 - Pipe Laying | Completed | 2025-01-16 09:36 | 2025-03-11 02:24 | 2025-01-15 06:35 | 2025-03-11 03:10 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.012734 | 389865.35
TASK-0005 | Z01-PIP-002 | Zone 01 - Pipe Laying - Activity 2 | WBS-0004 | Zone 01 - Pipe Laying | Completed | 2025-03-11 02:24 | 2025-05-03 19:12 | 2025-03-11 08:16 | 2025-05-05 02:18 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.060507 | 1852455.65
TASK-0006 | Z01-BAC-001 | Zone 01 - Backfill - Activity 1 | WBS-0005 | Zone 01 - Backfill | Completed | 2025-05-03 19:12 | 2025-06-26 12:00 | 2025-05-02 16:21 | 2025-06-27 00:51 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.006781 | 207602.08
TASK-0007 | Z01-BAC-002 | Zone 01 - Backfill - Activity 2 | WBS-0005 | Zone 01 - Backfill | Completed | 2025-06-26 12:00 | 2025-08-19 04:48 | 2025-06-27 12:50 | 2025-08-17 03:47 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.0060017 | 183744.12
TASK-0008 | Z01-REI-001 | Zone 01 - Reinstatement - Activity 1 | WBS-0006 | Zone 01 - Reinstatement | Completed | 2025-08-19 04:48 | 2025-10-11 21:36 | 2025-08-18 07:28 | 2025-10-10 04:36 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.0012822 | 39254.95
TASK-0009 | Z01-REI-002 | Zone 01 - Reinstatement - Activity 2 | WBS-0006 | Zone 01 - Reinstatement | Completed | 2025-10-11 21:36 | 2025-12-04 14:24 | 2025-10-10 07:24 | 2025-12-03 21:06 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.00090391 | 27673.5
TASK-0010 | Z01-TES-001 | Zone 01 - Testing & Commissioning - Activity 1 | WBS-0007 | Zone 01 - Testing & Commissioning | Completed | 2025-12-04 14:24 | 2026-01-27 07:12 | 2025-12-05 00:21 | 2026-01-29 03:25 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.0090909 | 278322.287
TASK-0011 | Z01-TES-002 | Zone 01 - Testing & Commissioning - Activity 2 | WBS-0007 | Zone 01 - Testing & Commissioning | Completed | 2026-01-27 07:12 | 2026-03-22 | 2026-01-27 10:40 | 2026-03-24 20:07 | 53 | 0 | 100 | Zone 01 | 100 | 0 | 0.0090909 | 278322.287
TASK-0012 | Z02-EXC-001 | Zone 02 - Excavation - Activity 1 | WBS-0009 | Zone 02 - Excavation | In Progress | 2024-10-16 | 2024-12-07 04:48 | 2024-10-18 03:31 |  | 52 | 3.125 | 93.8 | Zone 02 | 100 | -6.2 | 0.0002519 | 7711.9
TASK-0013 | Z02-EXC-002 | Zone 02 - Excavation - Activity 2 | WBS-0009 | Zone 02 - Excavation | Completed | 2024-12-07 04:48 | 2025-01-28 09:36 | 2024-12-06 22:09 | 2025-01-27 04:03 | 52 | 0 | 100 | Zone 02 | 100 | 0 | 0.00048384 | 14813.05
TASK-0014 | Z02-PIP-001 | Zone 02 - Pipe Laying - Activity 1 | WBS-0010 | Zone 02 - Pipe Laying | In Progress | 2025-01-28 09:36 | 2025-03-21 14:24 | 2025-01-30 06:22 |  | 52 | 1.75 | 96.53 | Zone 02 | 100 | -3.47 | 0.016533 | 506164.6
TASK-0015 | Z02-PIP-002 | Zone 02 - Pipe Laying - Activity 2 | WBS-0010 | Zone 02 - Pipe Laying | Completed | 2025-03-21 14:24 | 2025-05-12 19:12 | 2025-03-22 07:59 | 2025-05-12 07:41 | 52 | 0 | 100 | Zone 02 | 100 | 0 | 0.026056 | 797703.95
TASK-0016 | Z02-BAC-001 | Zone 02 - Backfill - Activity 1 | WBS-0011 | Zone 02 - Backfill | Completed | 2025-05-12 19:12 | 2025-06-16 14:24 | 2025-05-12 03:00 | 2025-06-16 00:30 | 34 | 0 | 100 | Zone 02 | 100 | 0 | 0.0020548 | 62909.56
TASK-0017 | Z02-BAC-002 | Zone 02 - Backfill - Activity 2 | WBS-0011 | Zone 02 - Backfill | In Progress | 2025-06-16 14:24 | 2025-07-21 09:36 | 2025-06-18 00:25 |  | 34 | 0.75 | 97.55 | Zone 02 | 100 | -2.45 | 0.0069076 | 211480.64
TASK-0018 | Z02-BAC-003 | Zone 02 - Backfill - Activity 3 | WBS-0011 | Zone 02 - Backfill | In Progress | 2025-07-21 09:36 | 2025-08-25 04:48 | 2025-07-20 06:08 |  | 34 | 1.5 | 95.23 | Zone 02 | 100 | -4.77 | 0.0061641 | 188715.24
TASK-0019 | Z02-REI-001 | Zone 02 - Reinstatement - Activity 1 | WBS-0012 | Zone 02 - Reinstatement | In Progress | 2025-08-25 04:48 | 2025-10-16 09:36 | 2025-08-24 13:11 |  | 52 | 4.375 | 91.56 | Zone 02 | 100 | -8.44 | 0.00047498 | 14541.65
TASK-0020 | Z02-REI-002 | Zone 02 - Reinstatement - Activity 2 | WBS-0012 | Zone 02 - Reinstatement | In Progress | 2025-10-16 09:36 | 2025-12-07 14:24 | 2025-10-16 00:30 |  | 52 | 7.5 | 85.49 | Zone 02 | 100 | -14.51 | 0.00059562 | 18235.25
TASK-0021 | Z02-TES-001 | Zone 02 - Testing & Commissioning - Activity 1 | WBS-0013 | Zone 02 - Testing & Commissioning | Completed | 2025-12-07 14:24 | 2026-01-28 19:12 | 2025-12-08 05:02 | 2026-01-28 09:42 | 52 | 0 | 100 | Zone 02 | 100 | 0 | 0.0090909 | 278322.287
TASK-0022 | Z02-TES-002 | Zone 02 - Testing & Commissioning - Activity 2 | WBS-0013 | Zone 02 - Testing & Commissioning | In Progress | 2026-01-28 19:12 | 2026-03-22 | 2026-01-31 12:20 |  | 52 | 7.625 | 85.27 | Zone 02 | 100 | -14.73 | 0.0090909 | 278322.287
TASK-0023 | Z03-EXC-001 | Zone 03 - Excavation - Activity 1 | WBS-0015 | Zone 03 - Excavation | In Progress | 2024-10-31 | 2024-12-20 16:48 | 2024-10-30 23:28 |  | 50 | 9.25 | 81.39 | Zone 03 | 100 | -18.61 | 0.0001657 | 5072.9
TASK-0024 | Z03-EXC-002 | Zone 03 - Excavation - Activity 2 | WBS-0015 | Zone 03 - Excavation | In Progress | 2024-12-20 16:48 | 2025-02-09 09:36 | 2024-12-19 09:33 |  | 50 | 15.625 | 68.57 | Zone 03 | 100 | -31.43 | 0.00050801 | 15552.95
TASK-0025 | Z03-PIP-001 | Zone 03 - Pipe Laying - Activity 1 | WBS-0016 | Zone 03 - Pipe Laying | In Progress | 2025-02-09 09:36 | 2025-03-15 04:48 | 2025-02-10 07:45 |  | 33 | 9.375 | 71.57 | Zone 03 | 100 | -28.43 | 0.04618 | 1413818.75
TASK-0026 | Z03-PIP-002 | Zone 03 - Pipe Laying - Activity 2 | WBS-0016 | Zone 03 - Pipe Laying | In Progress | 2025-03-15 04:48 | 2025-04-18 | 2025-03-14 07:07 |  | 33 | 8.25 | 74.99 | Zone 03 | 100 | -25.01 | 0.016799 | 514305.95
TASK-0027 | Z03-PIP-003 | Zone 03 - Pipe Laying - Activity 3 | WBS-0016 | Zone 03 - Pipe Laying | In Progress | 2025-04-18 | 2025-05-21 19:12 | 2025-04-16 10:54 |  | 33 | 7.25 | 77.74 | Zone 03 | 100 | -22.26 | 0.07103 | 2174609.65
TASK-0028 | Z03-BAC-001 | Zone 03 - Backfill - Activity 1 | WBS-0017 | Zone 03 - Backfill | In Progress | 2025-05-21 19:12 | 2025-07-11 12:00 | 2025-05-20 14:23 |  | 50 | 15.5 | 68.82 | Zone 03 | 100 | -31.18 | 0.0012022 | 36807.12
TASK-0029 | Z03-BAC-002 | Zone 03 - Backfill - Activity 2 | WBS-0017 | Zone 03 - Backfill | In Progress | 2025-07-11 12:00 | 2025-08-31 04:48 | 2025-07-11 10:10 |  | 50 | 10 | 79.91 | Zone 03 | 100 | -20.09 | 0.0026594 | 81418.96
TASK-0030 | Z03-REI-001 | Zone 03 - Reinstatement - Activity 1 | WBS-0018 | Zone 03 - Reinstatement | In Progress | 2025-08-31 04:48 | 2025-10-20 21:36 | 2025-09-03 01:19 |  | 50 | 10.875 | 78.23 | Zone 03 | 100 | -21.77 | 0.00031092 | 9519
TASK-0031 | Z03-REI-002 | Zone 03 - Reinstatement - Activity 2 | WBS-0018 | Zone 03 - Reinstatement | In Progress | 2025-10-20 21:36 | 2025-12-10 14:24 | 2025-10-19 11:20 |  | 50 | 8.875 | 82.01 | Zone 03 | 100 | -17.99 | 0.00078872 | 24147.1
TASK-0032 | Z03-TES-001 | Zone 03 - Testing & Commissioning - Activity 1 | WBS-0019 | Zone 03 - Testing & Commissioning | In Progress | 2025-12-10 14:24 | 2026-01-30 07:12 | 2025-12-10 07:13 |  | 50 | 7.875 | 84.21 | Zone 03 | 100 | -15.79 | 0.0090909 | 278322.287
TASK-0033 | Z03-TES-002 | Zone 03 - Testing & Commissioning - Activity 2 | WBS-0019 | Zone 03 - Testing & Commissioning | In Progress | 2026-01-30 07:12 | 2026-03-22 | 2026-01-30 13:38 |  | 50 | 12 | 75.87 | Zone 03 | 100 | -24.13 | 0.0090909 | 278322.287
TASK-0034 | Z04-EXC-001 | Zone 04 - Excavation - Activity 1 | WBS-0021 | Zone 04 - Excavation | In Progress | 2024-11-15 | 2024-12-17 19:12 | 2024-11-15 12:55 |  | 32 | 11.5 | 64.05 | Zone 04 | 100 | -35.95 | 0.00050774 | 15544.55
TASK-0035 | Z04-EXC-002 | Zone 04 - Excavation - Activity 2 | WBS-0021 | Zone 04 - Excavation | In Progress | 2024-12-17 19:12 | 2025-01-19 14:24 | 2024-12-17 07:00 |  | 32 | 10.625 | 66.76 | Zone 04 | 100 | -33.24 | 0.00031468 | 9634.1
TASK-0036 | Z04-EXC-003 | Zone 04 - Excavation - Activity 3 | WBS-0021 | Zone 04 - Excavation | In Progress | 2025-01-19 14:24 | 2025-02-21 09:36 | 2025-01-18 08:44 |  | 32 | 12.625 | 60.22 | Zone 04 | 100 | -39.78 | 0.00052666 | 16123.8
TASK-0037 | Z04-PIP-001 | Zone 04 - Pipe Laying - Activity 1 | WBS-0022 | Zone 04 - Pipe Laying | In Progress | 2025-02-21 09:36 | 2025-03-26 04:48 | 2025-02-24 00:17 |  | 32 | 9.875 | 68.84 | Zone 04 | 100 | -31.16 | 0.058613 | 1794473.15
TASK-0038 | Z04-PIP-002 | Zone 04 - Pipe Laying - Activity 2 | WBS-0022 | Zone 04 - Pipe Laying | In Progress | 2025-03-26 04:48 | 2025-04-28 | 2025-03-26 15:25 |  | 32 | 12.75 | 59.97 | Zone 04 | 100 | -40.03 | 0.027652 | 846581.2
TASK-0039 | Z04-PIP-003 | Zone 04 - Pipe Laying - Activity 3 | WBS-0022 | Zone 04 - Pipe Laying | In Progress | 2025-04-28 | 2025-05-30 19:12 | 2025-04-30 09:26 |  | 32 | 10.125 | 68.23 | Zone 04 | 100 | -31.77 | 0.057457 | 1759082.85
TASK-0040 | Z04-BAC-001 | Zone 04 - Backfill - Activity 1 | WBS-0023 | Zone 04 - Backfill | In Progress | 2025-05-30 19:12 | 2025-07-19 | 2025-06-02 04:33 |  | 49 | 26.125 | 46.45 | Zone 04 | 100 | -53.55 | 0.0025636 | 78486.24
TASK-0041 | Z04-BAC-002 | Zone 04 - Backfill - Activity 2 | WBS-0023 | Zone 04 - Backfill | In Progress | 2025-07-19 | 2025-09-06 04:48 | 2025-07-19 10:19 |  | 49 | 25.875 | 47.14 | Zone 04 | 100 | -52.86 | 0.004235 | 129657.08
TASK-0042 | Z04-REI-001 | Zone 04 - Reinstatement - Activity 1 | WBS-0024 | Zone 04 - Reinstatement | In Progress | 2025-09-06 04:48 | 2025-10-09 | 2025-09-04 20:12 |  | 32 | 11.375 | 64.15 | Zone 04 | 100 | -35.85 | 0.00043603 | 13349.4
TASK-0043 | Z04-REI-002 | Zone 04 - Reinstatement - Activity 2 | WBS-0024 | Zone 04 - Reinstatement | In Progress | 2025-10-09 | 2025-11-10 19:12 | 2025-10-07 19:48 |  | 32 | 10 | 68.67 | Zone 04 | 100 | -31.33 | 0.0015447 | 47292.9
TASK-0044 | Z04-REI-003 | Zone 04 - Reinstatement - Activity 3 | WBS-0024 | Zone 04 - Reinstatement | In Progress | 2025-11-10 19:12 | 2025-12-13 14:24 | 2025-11-10 21:58 |  | 32 | 10.5 | 66.81 | Zone 04 | 100 | -33.19 | 0.00076691 | 23479.25
TASK-0045 | Z04-TES-001 | Zone 04 - Testing & Commissioning - Activity 1 | WBS-0025 | Zone 04 - Testing & Commissioning | In Progress | 2025-12-13 14:24 | 2026-01-15 09:36 | 2025-12-15 01:11 |  | 32 | 11.5 | 63.88 | Zone 04 | 100 | -36.12 | 0.0090909 | 278322.287
TASK-0046 | Z04-TES-002 | Zone 04 - Testing & Commissioning - Activity 2 | WBS-0025 | Zone 04 - Testing & Commissioning | In Progress | 2026-01-15 09:36 | 2026-02-17 04:48 | 2026-01-16 18:12 |  | 32 | 14.375 | 54.97 | Zone 04 | 100 | -45.03 | 0.0090909 | 278322.287
TASK-0047 | Z04-TES-003 | Zone 04 - Testing & Commissioning - Activity 3 | WBS-0025 | Zone 04 - Testing & Commissioning | In Progress | 2026-02-17 04:48 | 2026-03-22 | 2026-02-17 18:54 |  | 32 | 14 | 55.95 | Zone 04 | 100 | -44.05 | 0.0090909 | 278322.287
TASK-0048 | Z05-EXC-001 | Zone 05 - Excavation - Activity 1 | WBS-0027 | Zone 05 - Excavation | In Progress | 2024-11-30 | 2025-01-16 16:48 | 2024-11-29 16:34 |  | 47 | 27.875 | 40.62 | Zone 05 | 100 | -59.38 | 0.00011941 | 3655.75
TASK-0049 | Z05-EXC-002 | Zone 05 - Excavation - Activity 2 | WBS-0027 | Zone 05 - Excavation | In Progress | 2025-01-16 16:48 | 2025-03-05 09:36 | 2025-01-17 15:24 |  | 47 | 24 | 48.85 | Zone 05 | 100 | -51.15 | 0.00023109 | 7074.9
TASK-0050 | Z05-PIP-001 | Zone 05 - Pipe Laying - Activity 1 | WBS-0028 | Zone 05 - Pipe Laying | In Progress | 2025-03-05 09:36 | 2025-04-22 02:24 | 2025-03-03 16:39 |  | 47 | 22.125 | 52.7 | Zone 05 | 100 | -47.3 | 0.061656 | 1887614.45
TASK-0051 | Z05-PIP-002 | Zone 05 - Pipe Laying - Activity 2 | WBS-0028 | Zone 05 - Pipe Laying | In Progress | 2025-04-22 02:24 | 2025-06-08 19:12 | 2025-04-24 09:33 |  | 47 | 19.875 | 57.64 | Zone 05 | 100 | -42.36 | 0.038965 | 1192934.2
TASK-0052 | Z05-BAC-001 | Zone 05 - Backfill - Activity 1 | WBS-0029 | Zone 05 - Backfill | In Progress | 2025-06-08 19:12 | 2025-07-10 14:24 | 2025-06-10 03:28 |  | 31 | 18.25 | 40.95 | Zone 05 | 100 | -59.05 | 0.0016624 | 50894.76
TASK-0053 | Z05-BAC-002 | Zone 05 - Backfill - Activity 2 | WBS-0029 | Zone 05 - Backfill | In Progress | 2025-07-10 14:24 | 2025-08-11 09:36 | 2025-07-12 05:12 |  | 31 | 15.875 | 48.48 | Zone 05 | 100 | -51.52 | 0.0054068 | 165530.68
TASK-0054 | Z05-BAC-003 | Zone 05 - Backfill - Activity 3 | WBS-0029 | Zone 05 - Backfill | In Progress | 2025-08-11 09:36 | 2025-09-12 04:48 | 2025-08-10 14:45 |  | 31 | 15.625 | 49.41 | Zone 05 | 100 | -50.59 | 0.0036222 | 110895.96
TASK-0055 | Z05-REI-001 | Zone 05 - Reinstatement - Activity 1 | WBS-0030 | Zone 05 - Reinstatement | In Progress | 2025-09-12 04:48 | 2025-10-29 21:36 | 2025-09-10 16:25 |  | 47 | 28.25 | 39.76 | Zone 05 | 100 | -60.24 | 0.0013583 | 41586.25
TASK-0056 | Z05-REI-002 | Zone 05 - Reinstatement - Activity 2 | WBS-0030 | Zone 05 - Reinstatement | In Progress | 2025-10-29 21:36 | 2025-12-16 14:24 | 2025-10-29 22:55 |  | 47 | 26.375 | 43.86 | Zone 05 | 100 | -56.14 | 0.00042074 | 12881.05
TASK-0057 | Z05-TES-001 | Zone 05 - Testing & Commissioning - Activity 1 | WBS-0031 | Zone 05 - Testing & Commissioning | In Progress | 2025-12-16 14:24 | 2026-01-17 09:36 | 2025-12-17 19:56 |  | 31 | 15 | 51.34 | Zone 05 | 100 | -48.66 | 0.0090909 | 278322.287
TASK-0058 | Z05-TES-002 | Zone 05 - Testing & Commissioning - Activity 2 | WBS-0031 | Zone 05 - Testing & Commissioning | In Progress | 2026-01-17 09:36 | 2026-02-18 04:48 | 2026-01-17 02:18 |  | 31 | 17 | 45.07 | Zone 05 | 100 | -54.93 | 0.0090909 | 278322.287
TASK-0059 | Z05-TES-003 | Zone 05 - Testing & Commissioning - Activity 3 | WBS-0031 | Zone 05 - Testing & Commissioning | In Progress | 2026-02-18 04:48 | 2026-03-22 | 2026-02-17 03:37 |  | 31 | 18.125 | 41.22 | Zone 05 | 100 | -58.78 | 0.0090909 | 278322.287
TASK-0060 | Z06-EXC-001 | Zone 06 - Excavation - Activity 1 | WBS-0033 | Zone 06 - Excavation | In Progress | 2024-12-15 | 2025-01-30 04:48 | 2024-12-14 09:25 |  | 46 | 36.5 | 20.55 | Zone 06 | 100 | -79.45 | 0.0002742 | 8394.75
TASK-0061 | Z06-EXC-002 | Zone 06 - Excavation - Activity 2 | WBS-0033 | Zone 06 - Excavation | In Progress | 2025-01-30 04:48 | 2025-03-17 09:36 | 2025-01-28 13:50 |  | 46 | 31.25 | 31.86 | Zone 06 | 100 | -68.14 | 0.00018567 | 5684.35
TASK-0062 | Z06-PIP-001 | Zone 06 - Pipe Laying - Activity 1 | WBS-0034 | Zone 06 - Pipe Laying | In Progress | 2025-03-17 09:36 | 2025-05-02 14:24 | 2025-03-20 09:30 |  | 46 | 40.75 | 11.26 | Zone 06 | 100 | -88.74 | 0.070935 | 2171694.65
TASK-0063 | Z06-PIP-002 | Zone 06 - Pipe Laying - Activity 2 | WBS-0034 | Zone 06 - Pipe Laying | In Progress | 2025-05-02 14:24 | 2025-06-17 19:12 | 2025-05-05 05:33 |  | 46 | 30.25 | 34.22 | Zone 06 | 100 | -65.78 | 0.034733 | 1063356.9
TASK-0064 | Z06-BAC-001 | Zone 06 - Backfill - Activity 1 | WBS-0035 | Zone 06 - Backfill | In Progress | 2025-06-17 19:12 | 2025-08-03 | 2025-06-18 04:57 |  | 46 | 36.625 | 20.16 | Zone 06 | 100 | -79.84 | 0.0036497 | 111736.52
TASK-0065 | Z06-BAC-002 | Zone 06 - Backfill - Activity 2 | WBS-0035 | Zone 06 - Backfill | In Progress | 2025-08-03 | 2025-09-18 04:48 | 2025-08-01 19:45 |  | 46 | 31 | 32.56 | Zone 06 | 100 | -67.44 | 0.0045567 | 139504.12
TASK-0066 | Z06-REI-001 | Zone 06 - Reinstatement - Activity 1 | WBS-0036 | Zone 06 - Reinstatement | In Progress | 2025-09-18 04:48 | 2025-11-03 09:36 | 2025-09-20 02:53 |  | 46 | 38.25 | 16.63 | Zone 06 | 100 | -83.37 | 0.00037131 | 11367.7
TASK-0067 | Z06-REI-002 | Zone 06 - Reinstatement - Activity 2 | WBS-0036 | Zone 06 - Reinstatement | In Progress | 2025-11-03 09:36 | 2025-12-19 14:24 | 2025-11-04 21:11 |  | 46 | 38 | 17.13 | Zone 06 | 100 | -82.87 | 0.0015078 | 46162.4
TASK-0068 | Z06-TES-001 | Zone 06 - Testing & Commissioning - Activity 1 | WBS-0037 | Zone 06 - Testing & Commissioning | In Progress | 2025-12-19 14:24 | 2026-01-19 09:36 | 2025-12-18 08:58 |  | 30 | 21.5 | 27.96 | Zone 06 | 100 | -72.04 | 0.0090909 | 278322.287
TASK-0069 | Z06-TES-002 | Zone 06 - Testing & Commissioning - Activity 2 | WBS-0037 | Zone 06 - Testing & Commissioning | In Progress | 2026-01-19 09:36 | 2026-02-19 04:48 | 2026-01-17 16:37 |  | 30 | 25.25 | 15.44 | Zone 06 | 100 | -84.56 | 0.0090909 | 278322.287
TASK-0070 | Z06-TES-003 | Zone 06 - Testing & Commissioning - Activity 3 | WBS-0037 | Zone 06 - Testing & Commissioning | In Progress | 2026-02-19 04:48 | 2026-03-22 | 2026-02-18 18:25 |  | 30 | 26.5 | 11.52 | Zone 06 | 100 | -88.48 | 0.0090909 | 278322.287
TASK-0071 | Z07-EXC-001 | Zone 07 - Excavation - Activity 1 | WBS-0039 | Zone 07 - Excavation | In Progress | 2024-12-30 | 2025-01-28 19:12 | 2025-01-01 14:19 |  | 29 | 28.375 | 1.92 | Zone 07 | 100 | -98.08 | 0.00033609 | 10289.65
TASK-0072 | Z07-EXC-002 | Zone 07 - Excavation - Activity 2 | WBS-0039 | Zone 07 - Excavation | Not Started | 2025-01-28 19:12 | 2025-02-27 14:24 |  |  | 29 | 29 | 0 | Zone 07 | 100 | -100 | 8.6564e-05 | 2650.2
TASK-0073 | Z07-EXC-003 | Zone 07 - Excavation - Activity 3 | WBS-0039 | Zone 07 - Excavation | Not Started | 2025-02-27 14:24 | 2025-03-29 09:36 |  |  | 29 | 29 | 0 | Zone 07 | 100 | -100 | 0.00031585 | 9669.8
TASK-0074 | Z07-PIP-001 | Zone 07 - Pipe Laying - Activity 1 | WBS-0040 | Zone 07 - Pipe Laying | In Progress | 2025-03-29 09:36 | 2025-05-13 02:24 | 2025-03-30 18:37 |  | 44 | 41.75 | 4.88 | Zone 07 | 100 | -95.12 | 0.023385 | 715940.85
TASK-0075 | Z07-PIP-002 | Zone 07 - Pipe Laying - Activity 2 | WBS-0040 | Zone 07 - Pipe Laying | In Progress | 2025-05-13 02:24 | 2025-06-26 19:12 | 2025-05-15 19:23 |  | 44 | 43.875 | 0.09 | Zone 07 | 100 | -99.91 | 0.04397 | 1346156
TASK-0076 | Z07-BAC-001 | Zone 07 - Backfill - Activity 1 | WBS-0041 | Zone 07 - Backfill | In Progress | 2025-06-26 19:12 | 2025-08-10 12:00 | 2025-06-24 23:58 |  | 44 | 42 | 4.47 | Zone 07 | 100 | -95.53 | 0.0022892 | 70085.96
TASK-0077 | Z07-BAC-002 | Zone 07 - Backfill - Activity 2 | WBS-0041 | Zone 07 - Backfill | In Progress | 2025-08-10 12:00 | 2025-09-24 04:48 | 2025-08-11 10:02 |  | 44 | 43.75 | 0.48 | Zone 07 | 100 | -99.52 | 0.00296 | 90620.88
TASK-0078 | Z07-REI-001 | Zone 07 - Reinstatement - Activity 1 | WBS-0042 | Zone 07 - Reinstatement | In Progress | 2025-09-24 04:48 | 2025-11-07 21:36 | 2025-09-23 05:18 |  | 44 | 38 | 13.37 | Zone 07 | 100 | -86.63 | 0.00025643 | 7850.8
TASK-0079 | Z07-REI-002 | Zone 07 - Reinstatement - Activity 2 | WBS-0042 | Zone 07 - Reinstatement | Not Started | 2025-11-07 21:36 | 2025-12-22 14:24 |  |  | 44 | 44 | 0 | Zone 07 | 100 | -100 | 0.0015493 | 47433.5
TASK-0080 | Z07-TES-001 | Zone 07 - Testing & Commissioning - Activity 1 | WBS-0043 | Zone 07 - Testing & Commissioning | In Progress | 2025-12-22 14:24 | 2026-02-05 07:12 | 2025-12-22 02:23 |  | 44 | 41 | 6.79 | Zone 07 | 100 | -93.21 | 0.0090909 | 278322.287
TASK-0081 | Z07-TES-002 | Zone 07 - Testing & Commissioning - Activity 2 | WBS-0043 | Zone 07 - Testing & Commissioning | In Progress | 2026-02-05 07:12 | 2026-03-22 | 2026-02-07 23:29 |  | 44 | 38.125 | 13.23 | Zone 07 | 100 | -86.77 | 0.0090909 | 278322.287
TASK-0082 | Z08-EXC-001 | Zone 08 - Excavation - Activity 1 | WBS-0045 | Zone 08 - Excavation | Not Started | 2025-01-14 | 2025-02-26 04:48 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 9.4852e-05 | 2903.95
TASK-0083 | Z08-EXC-002 | Zone 08 - Excavation - Activity 2 | WBS-0045 | Zone 08 - Excavation | Not Started | 2025-02-26 04:48 | 2025-04-10 09:36 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.00019359 | 5926.9
TASK-0084 | Z08-PIP-001 | Zone 08 - Pipe Laying - Activity 1 | WBS-0046 | Zone 08 - Pipe Laying | Not Started | 2025-04-10 09:36 | 2025-05-23 14:24 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.049487 | 1515053.9
TASK-0085 | Z08-PIP-002 | Zone 08 - Pipe Laying - Activity 2 | WBS-0046 | Zone 08 - Pipe Laying | Not Started | 2025-05-23 14:24 | 2025-07-05 19:12 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.020108 | 615601.85
TASK-0086 | Z08-BAC-001 | Zone 08 - Backfill - Activity 1 | WBS-0047 | Zone 08 - Backfill | Not Started | 2025-07-05 19:12 | 2025-08-18 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.0024571 | 75223.96
TASK-0087 | Z08-BAC-002 | Zone 08 - Backfill - Activity 2 | WBS-0047 | Zone 08 - Backfill | Not Started | 2025-08-18 | 2025-09-30 04:48 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.0049424 | 151314.24
TASK-0088 | Z08-REI-001 | Zone 08 - Reinstatement - Activity 1 | WBS-0048 | Zone 08 - Reinstatement | Not Started | 2025-09-30 04:48 | 2025-11-12 09:36 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.00083732 | 25634.8
TASK-0089 | Z08-REI-002 | Zone 08 - Reinstatement - Activity 2 | WBS-0048 | Zone 08 - Reinstatement | Not Started | 2025-11-12 09:36 | 2025-12-25 14:24 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.0013366 | 40921.25
TASK-0090 | Z08-TES-001 | Zone 08 - Testing & Commissioning - Activity 1 | WBS-0049 | Zone 08 - Testing & Commissioning | Not Started | 2025-12-25 14:24 | 2026-02-06 19:12 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.0090909 | 278322.287
TASK-0091 | Z08-TES-002 | Zone 08 - Testing & Commissioning - Activity 2 | WBS-0049 | Zone 08 - Testing & Commissioning | Not Started | 2026-02-06 19:12 | 2026-03-22 |  |  | 43 | 43 | 0 | Zone 08 | 100 | -100 | 0.0090909 | 278322.287

## WBS
wbs_id | wbs_name | parent_wbs_id | wbs_level | total_planned_cost | total_actual_cost
WBS-0001 | Al-Narjis Water Network - Phase 2 |  | 1 | 0 | 0
WBS-0002 | Zone 01 | WBS-0001 | 2 | 0 | 0
WBS-0003 | Zone 01 - Excavation | WBS-0002 | 3 | 31251.85 | 30264.15
WBS-0004 | Zone 01 - Pipe Laying | WBS-0002 | 3 | 2242321 | 2282746.25
WBS-0005 | Zone 01 - Backfill | WBS-0002 | 3 | 391346.2 | 387907.8
WBS-0006 | Zone 01 - Reinstatement | WBS-0002 | 3 | 66928.45 | 71350.7
WBS-0007 | Zone 01 - Testing & Commissioning | WBS-0002 | 3 | 0 | 0
WBS-0008 | Zone 02 | WBS-0001 | 2 | 0 | 0
WBS-0009 | Zone 02 - Excavation | WBS-0008 | 3 | 22524.95 | 22473.15
WBS-0010 | Zone 02 - Pipe Laying | WBS-0008 | 3 | 1303868.55 | 1323167.1
WBS-0011 | Zone 02 - Backfill | WBS-0008 | 3 | 463105.44 | 466948.72
WBS-0012 | Zone 02 - Reinstatement | WBS-0008 | 3 | 32776.9 | 26934.4
WBS-0013 | Zone 02 - Testing & Commissioning | WBS-0008 | 3 | 0 | 0
WBS-0014 | Zone 03 | WBS-0001 | 2 | 0 | 0
WBS-0015 | Zone 03 - Excavation | WBS-0014 | 3 | 20625.85 | 14764.05
WBS-0016 | Zone 03 - Pipe Laying | WBS-0014 | 3 | 4102734.35 | 3028317.25
WBS-0017 | Zone 03 - Backfill | WBS-0014 | 3 | 118226.08 | 93438.24
WBS-0018 | Zone 03 - Reinstatement | WBS-0014 | 3 | 33666.1 | 28949.35
WBS-0019 | Zone 03 - Testing & Commissioning | WBS-0014 | 3 | 0 | 0
WBS-0020 | Zone 04 | WBS-0001 | 2 | 0 | 0
WBS-0021 | Zone 04 - Excavation | WBS-0020 | 3 | 41302.45 | 25932.55
WBS-0022 | Zone 04 - Pipe Laying | WBS-0020 | 3 | 4400137.2 | 2829849.65
WBS-0023 | Zone 04 - Backfill | WBS-0020 | 3 | 208143.32 | 102552.52
WBS-0024 | Zone 04 - Reinstatement | WBS-0020 | 3 | 84121.55 | 57432.25
WBS-0025 | Zone 04 - Testing & Commissioning | WBS-0020 | 3 | 0 | 0
WBS-0026 | Zone 05 | WBS-0001 | 2 | 0 | 0
WBS-0027 | Zone 05 - Excavation | WBS-0026 | 3 | 10730.65 | 4920.3
WBS-0028 | Zone 05 - Pipe Laying | WBS-0026 | 3 | 3080548.65 | 1635513.35
WBS-0029 | Zone 05 - Backfill | WBS-0026 | 3 | 327321.4 | 155926.12
WBS-0030 | Zone 05 - Reinstatement | WBS-0026 | 3 | 54467.3 | 21295.2
WBS-0031 | Zone 05 - Testing & Commissioning | WBS-0026 | 3 | 0 | 0
WBS-0032 | Zone 06 | WBS-0001 | 2 | 0 | 0
WBS-0033 | Zone 06 - Excavation | WBS-0032 | 3 | 14079.1 | 3613.05
WBS-0034 | Zone 06 - Pipe Laying | WBS-0032 | 3 | 3235051.55 | 655902.05
WBS-0035 | Zone 06 - Backfill | WBS-0032 | 3 | 251240.64 | 69898.92
WBS-0036 | Zone 06 - Reinstatement | WBS-0032 | 3 | 57530.1 | 9846.75
WBS-0037 | Zone 06 - Testing & Commissioning | WBS-0032 | 3 | 0 | 0
WBS-0038 | Zone 07 | WBS-0001 | 2 | 0 | 0
WBS-0039 | Zone 07 - Excavation | WBS-0038 | 3 | 22609.65 | 207.2
WBS-0040 | Zone 07 - Pipe Laying | WBS-0038 | 3 | 2062096.85 | 33938.85
WBS-0041 | Zone 07 - Backfill | WBS-0038 | 3 | 160706.84 | 3531.92
WBS-0042 | Zone 07 - Reinstatement | WBS-0038 | 3 | 55284.3 | 1041.2
WBS-0043 | Zone 07 - Testing & Commissioning | WBS-0038 | 3 | 0 | 0
WBS-0044 | Zone 08 | WBS-0001 | 2 | 0 | 0
WBS-0045 | Zone 08 - Excavation | WBS-0044 | 3 | 8830.85 | 0
WBS-0046 | Zone 08 - Pipe Laying | WBS-0044 | 3 | 2130655.75 | 0
WBS-0047 | Zone 08 - Backfill | WBS-0044 | 3 | 226538.2 | 0
WBS-0048 | Zone 08 - Reinstatement | WBS-0044 | 3 | 66556.05 | 0
WBS-0049 | Zone 08 - Testing & Commissioning | WBS-0044 | 3 | 0 | 0

## Resources
task_id | task_name | wbs_id | rsrc_id | rsrc_name | rsrc_type | unit_of_measure | unit_price | target_qty | act_qty | remain_qty | target_cost | act_cost | ev_cost | cv | is_material
TASK-0001 | Zone 01 - Excavation - Activity 1 | WBS-0003 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 337.74 | 305.66 | 32.08 | 11820.9 | 10698.1 | 11820.9 | 1122.8 | TRUE
TASK-0002 | Zone 01 - Excavation - Activity 2 | WBS-0003 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 173.76 | 164.14 | 9.62 | 6081.6 | 5744.9 | 6081.6 | 336.7 | TRUE
TASK-0003 | Zone 01 - Excavation - Activity 3 | WBS-0003 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 381.41 | 394.89 | 0 | 13349.35 | 13821.15 | 13349.35 | -471.8 | TRUE
TASK-0004 | Zone 01 - Pipe Laying - Activity 1 | WBS-0004 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 451.48 | 414.18 | 37.3 | 83523.8 | 76623.3 | 83523.8 | 6900.5 | TRUE
TASK-0004 | Zone 01 - Pipe Laying - Activity 1 | WBS-0004 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 239.86 | 217.3 | 22.56 | 33580.4 | 30422 | 33580.4 | 3158.4 | TRUE
TASK-0004 | Zone 01 - Pipe Laying - Activity 1 | WBS-0004 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 148.39 | 148.55 | 0 | 12613.15 | 12626.75 | 12613.15 | -13.6 | TRUE
TASK-0004 | Zone 01 - Pipe Laying - Activity 1 | WBS-0004 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 61.94 | 58.21 | 3.73 | 260148 | 244482 | 260148 | 15666 | TRUE
TASK-0005 | Zone 01 - Pipe Laying - Activity 2 | WBS-0004 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 342.45 | 345.53 | 0 | 63353.25 | 63923.05 | 63353.25 | -569.8 | TRUE
TASK-0005 | Zone 01 - Pipe Laying - Activity 2 | WBS-0004 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 149.2 | 151.86 | 0 | 20888 | 21260.4 | 20888 | -372.4 | TRUE
TASK-0005 | Zone 01 - Pipe Laying - Activity 2 | WBS-0004 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 414.24 | 373.35 | 40.89 | 35210.4 | 31734.75 | 35210.4 | 3475.65 | TRUE
TASK-0005 | Zone 01 - Pipe Laying - Activity 2 | WBS-0004 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 412.62 | 428.97 | 0 | 1733004 | 1801674 | 1733004 | -68670 | TRUE
TASK-0006 | Zone 01 - Backfill - Activity 1 | WBS-0005 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 203.11 | 189.11 | 14 | 5687.08 | 5295.08 | 5687.08 | 392 | TRUE
TASK-0006 | Zone 01 - Backfill - Activity 1 | WBS-0005 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 480.75 | 465.04 | 15.71 | 201915 | 195316.8 | 201915 | 6598.2 | TRUE
TASK-0007 | Zone 01 - Backfill - Activity 2 | WBS-0005 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 91.74 | 84.34 | 7.4 | 2568.72 | 2361.52 | 2568.72 | 207.2 | TRUE
TASK-0007 | Zone 01 - Backfill - Activity 2 | WBS-0005 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 431.37 | 440.32 | 0 | 181175.4 | 184934.4 | 181175.4 | -3759 | TRUE
TASK-0008 | Zone 01 - Reinstatement - Activity 1 | WBS-0006 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 413.21 | 432.2 | 0 | 39254.95 | 41059 | 39254.95 | -1804.05 | TRUE
TASK-0009 | Zone 01 - Reinstatement - Activity 2 | WBS-0006 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 291.3 | 318.86 | 0 | 27673.5 | 30291.7 | 27673.5 | -2618.2 | TRUE
TASK-0012 | Zone 02 - Excavation - Activity 1 | WBS-0009 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 220.34 | 208.83 | 11.51 | 7711.9 | 7309.05 | 7233.7622 | -75.2878 | TRUE
TASK-0013 | Zone 02 - Excavation - Activity 2 | WBS-0009 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 423.23 | 433.26 | 0 | 14813.05 | 15164.1 | 14813.05 | -351.05 | TRUE
TASK-0014 | Zone 02 - Pipe Laying - Activity 1 | WBS-0010 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 437.77 | 429.12 | 8.65 | 80987.45 | 79387.2 | 78177.1855 | -1210.0145 | TRUE
TASK-0014 | Zone 02 - Pipe Laying - Activity 1 | WBS-0010 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 367.06 | 322.14 | 44.92 | 51388.4 | 45099.6 | 49605.2225 | 4505.6225 | TRUE
TASK-0014 | Zone 02 - Pipe Laying - Activity 1 | WBS-0010 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 152.55 | 141.05 | 11.5 | 12966.75 | 11989.25 | 12516.8038 | 527.5538 | TRUE
TASK-0014 | Zone 02 - Pipe Laying - Activity 1 | WBS-0010 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 85.91 | 78.5 | 7.41 | 360822 | 329700 | 348301.4766 | 18601.4766 | TRUE
TASK-0015 | Zone 02 - Pipe Laying - Activity 2 | WBS-0010 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 95.45 | 91.21 | 4.24 | 17658.25 | 16873.85 | 17658.25 | 784.4 | TRUE
TASK-0015 | Zone 02 - Pipe Laying - Activity 2 | WBS-0010 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 336.06 | 326.98 | 9.08 | 47048.4 | 45777.2 | 47048.4 | 1271.2 | TRUE
TASK-0015 | Zone 02 - Pipe Laying - Activity 2 | WBS-0010 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 216.58 | 204 | 12.58 | 18409.3 | 17340 | 18409.3 | 1069.3 | TRUE
TASK-0015 | Zone 02 - Pipe Laying - Activity 2 | WBS-0010 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 170.14 | 185 | 0 | 714588 | 777000 | 714588 | -62412 | TRUE
TASK-0016 | Zone 02 - Backfill - Activity 1 | WBS-0011 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 341.62 | 349.08 | 0 | 9565.36 | 9774.24 | 9565.36 | -208.88 | TRUE
TASK-0016 | Zone 02 - Backfill - Activity 1 | WBS-0011 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 127.01 | 132.83 | 0 | 53344.2 | 55788.6 | 53344.2 | -2444.4 | TRUE
TASK-0017 | Zone 02 - Backfill - Activity 2 | WBS-0011 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 123.53 | 117.6 | 5.93 | 3458.84 | 3292.8 | 3374.0984 | 81.2984 | TRUE
TASK-0017 | Zone 02 - Backfill - Activity 2 | WBS-0011 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 495.29 | 496.68 | 0 | 208021.8 | 208605.6 | 202925.2659 | -5680.3341 | TRUE
TASK-0018 | Zone 02 - Backfill - Activity 3 | WBS-0011 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 300.63 | 296.86 | 3.77 | 8417.64 | 8312.08 | 8016.1186 | -295.9614 | TRUE
TASK-0018 | Zone 02 - Backfill - Activity 3 | WBS-0011 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 429.28 | 431.37 | 0 | 180297.6 | 181175.4 | 171697.4045 | -9477.9955 | TRUE
TASK-0019 | Zone 02 - Reinstatement - Activity 1 | WBS-0012 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 153.07 | 127.04 | 26.03 | 14541.65 | 12068.8 | 13314.3347 | 1245.5347 | TRUE
TASK-0020 | Zone 02 - Reinstatement - Activity 2 | WBS-0012 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 191.95 | 156.48 | 35.47 | 18235.25 | 14865.6 | 15589.3152 | 723.7152 | TRUE
TASK-0023 | Zone 03 - Excavation - Activity 1 | WBS-0015 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 144.94 | 128.42 | 16.52 | 5072.9 | 4494.7 | 4128.8333 | -365.8667 | TRUE
TASK-0024 | Zone 03 - Excavation - Activity 2 | WBS-0015 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 444.37 | 293.41 | 150.96 | 15552.95 | 10269.35 | 10664.6578 | 395.3078 | TRUE
TASK-0025 | Zone 03 - Pipe Laying - Activity 1 | WBS-0016 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 344.95 | 241.73 | 103.22 | 63815.75 | 44720.05 | 45672.9323 | 952.8823 | TRUE
TASK-0025 | Zone 03 - Pipe Laying - Activity 1 | WBS-0016 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 461.55 | 327.61 | 133.94 | 64617 | 45865.4 | 46246.3869 | 380.9869 | TRUE
TASK-0025 | Zone 03 - Pipe Laying - Activity 1 | WBS-0016 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 169.2 | 114.96 | 54.24 | 14382 | 9771.6 | 10293.1974 | 521.5974 | TRUE
TASK-0025 | Zone 03 - Pipe Laying - Activity 1 | WBS-0016 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 302.62 | 206.31 | 96.31 | 1271004 | 866502 | 909657.5628 | 43155.5628 | TRUE
TASK-0026 | Zone 03 - Pipe Laying - Activity 2 | WBS-0016 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 313.06 | 253.44 | 59.62 | 57916.1 | 46886.4 | 43431.2834 | -3455.1166 | TRUE
TASK-0026 | Zone 03 - Pipe Laying - Activity 2 | WBS-0016 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 229.73 | 162.6 | 67.13 | 32162.2 | 22764 | 24118.4338 | 1354.4338 | TRUE
TASK-0026 | Zone 03 - Pipe Laying - Activity 2 | WBS-0016 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 498.89 | 374.83 | 124.06 | 42405.65 | 31860.55 | 31799.9969 | -60.5531 | TRUE
TASK-0026 | Zone 03 - Pipe Laying - Activity 2 | WBS-0016 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 90.91 | 62 | 28.91 | 381822 | 260400 | 286328.3178 | 25928.3178 | TRUE
TASK-0027 | Zone 03 - Pipe Laying - Activity 3 | WBS-0016 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 99.34 | 79.2 | 20.14 | 18377.9 | 14652 | 14286.9795 | -365.0205 | TRUE
TASK-0027 | Zone 03 - Pipe Laying - Activity 3 | WBS-0016 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 406.44 | 311.05 | 95.39 | 56901.6 | 43547 | 44235.3038 | 688.3038 | TRUE
TASK-0027 | Zone 03 - Pipe Laying - Activity 3 | WBS-0016 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 78.59 | 59.65 | 18.94 | 6680.15 | 5070.25 | 5193.1486 | 122.8986 | TRUE
TASK-0027 | Zone 03 - Pipe Laying - Activity 3 | WBS-0016 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 498.25 | 389.59 | 108.66 | 2092650 | 1636278 | 1626826.11 | -9451.89 | TRUE
TASK-0028 | Zone 03 - Backfill - Activity 1 | WBS-0017 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 486.99 | 359.33 | 127.66 | 13635.72 | 10061.24 | 9384.1025 | -677.1375 | TRUE
TASK-0028 | Zone 03 - Backfill - Activity 1 | WBS-0017 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 55.17 | 39.64 | 15.53 | 23171.4 | 16648.8 | 15946.5575 | -702.2425 | TRUE
TASK-0029 | Zone 03 - Backfill - Activity 2 | WBS-0017 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 356.77 | 287.2 | 69.57 | 9989.56 | 8041.6 | 7982.6574 | -58.9426 | TRUE
TASK-0029 | Zone 03 - Backfill - Activity 2 | WBS-0017 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 170.07 | 139.73 | 30.34 | 71429.4 | 58686.6 | 57079.2335 | -1607.3665 | TRUE
TASK-0030 | Zone 03 - Reinstatement - Activity 1 | WBS-0018 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 100.2 | 77.36 | 22.84 | 9519 | 7349.2 | 7446.7137 | 97.5137 | TRUE
TASK-0031 | Zone 03 - Reinstatement - Activity 2 | WBS-0018 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 254.18 | 227.37 | 26.81 | 24147.1 | 21600.15 | 19803.0367 | -1797.1133 | TRUE
TASK-0034 | Zone 04 - Excavation - Activity 1 | WBS-0021 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 444.13 | 271 | 173.13 | 15544.55 | 9485 | 9956.2843 | 471.2843 | TRUE
TASK-0035 | Zone 04 - Excavation - Activity 2 | WBS-0021 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 275.26 | 171.95 | 103.31 | 9634.1 | 6018.25 | 6431.7252 | 413.4752 | TRUE
TASK-0036 | Zone 04 - Excavation - Activity 3 | WBS-0021 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 460.68 | 297.98 | 162.7 | 16123.8 | 10429.3 | 9709.7524 | -719.5476 | TRUE
TASK-0037 | Zone 04 - Pipe Laying - Activity 1 | WBS-0022 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 184.3 | 130.4 | 53.9 | 34095.5 | 24124 | 23471.3422 | -652.6578 | TRUE
TASK-0037 | Zone 04 - Pipe Laying - Activity 1 | WBS-0022 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 324.04 | 207.58 | 116.46 | 45365.6 | 29061.2 | 31229.679 | 2168.479 | TRUE
TASK-0037 | Zone 04 - Pipe Laying - Activity 1 | WBS-0022 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 393.13 | 272.76 | 120.37 | 33416.05 | 23184.6 | 23003.6088 | -180.9912 | TRUE
TASK-0037 | Zone 04 - Pipe Laying - Activity 1 | WBS-0022 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 400.38 | 277.29 | 123.09 | 1681596 | 1164618 | 1157610.6864 | -7007.3136 | TRUE
TASK-0038 | Zone 04 - Pipe Laying - Activity 2 | WBS-0022 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 50.26 | 29.08 | 21.18 | 9298.1 | 5379.8 | 5576.0706 | 196.2706 | TRUE
TASK-0038 | Zone 04 - Pipe Laying - Activity 2 | WBS-0022 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 58.76 | 38.26 | 20.5 | 8226.4 | 5356.4 | 4933.3721 | -423.0279 | TRUE
TASK-0038 | Zone 04 - Pipe Laying - Activity 2 | WBS-0022 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 445.42 | 284.84 | 160.58 | 37860.7 | 24211.4 | 22705.0618 | -1506.3382 | TRUE
TASK-0038 | Zone 04 - Pipe Laying - Activity 2 | WBS-0022 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 188.38 | 102.98 | 85.4 | 791196 | 432516 | 474480.2412 | 41964.2412 | TRUE
TASK-0039 | Zone 04 - Pipe Laying - Activity 3 | WBS-0022 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 445.1 | 330.84 | 114.26 | 82343.5 | 61205.4 | 56182.9701 | -5022.4299 | TRUE
TASK-0039 | Zone 04 - Pipe Laying - Activity 3 | WBS-0022 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 88.54 | 60.24 | 28.3 | 12395.6 | 8433.6 | 8457.5179 | 23.9179 | TRUE
TASK-0039 | Zone 04 - Pipe Laying - Activity 3 | WBS-0022 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 81.15 | 58.25 | 22.9 | 6897.75 | 4951.25 | 4706.3348 | -244.9152 | TRUE
TASK-0039 | Zone 04 - Pipe Laying - Activity 3 | WBS-0022 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 394.63 | 249.24 | 145.39 | 1657446 | 1046808 | 1130875.4058 | 84067.4058 | TRUE
TASK-0040 | Zone 04 - Backfill - Activity 1 | WBS-0023 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 263.88 | 123.79 | 140.09 | 7388.64 | 3466.12 | 3432.0233 | -34.0967 | TRUE
TASK-0040 | Zone 04 - Backfill - Activity 1 | WBS-0023 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 169.28 | 84.49 | 84.79 | 71097.6 | 35485.8 | 33024.8352 | -2460.9648 | TRUE
TASK-0041 | Zone 04 - Backfill - Activity 2 | WBS-0023 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 240.41 | 106.8 | 133.61 | 6731.48 | 2990.4 | 3173.2197 | 182.8197 | TRUE
TASK-0041 | Zone 04 - Backfill - Activity 2 | WBS-0023 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 292.68 | 144.31 | 148.37 | 122925.6 | 60610.2 | 57947.1278 | -2663.0722 | TRUE
TASK-0042 | Zone 04 - Reinstatement - Activity 1 | WBS-0024 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 140.52 | 86.75 | 53.77 | 13349.4 | 8241.25 | 8563.6401 | 322.3901 | TRUE
TASK-0043 | Zone 04 - Reinstatement - Activity 2 | WBS-0024 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 497.82 | 352.1 | 145.72 | 47292.9 | 33449.5 | 32476.0344 | -973.4656 | TRUE
TASK-0044 | Zone 04 - Reinstatement - Activity 3 | WBS-0024 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 247.15 | 165.7 | 81.45 | 23479.25 | 15741.5 | 15686.4869 | -55.0131 | TRUE
TASK-0048 | Zone 05 - Excavation - Activity 1 | WBS-0027 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 104.45 | 40.09 | 64.36 | 3655.75 | 1403.15 | 1484.9657 | 81.8157 | TRUE
TASK-0049 | Zone 05 - Excavation - Activity 2 | WBS-0027 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 202.14 | 100.49 | 101.65 | 7074.9 | 3517.15 | 3456.0887 | -61.0613 | TRUE
TASK-0050 | Zone 05 - Pipe Laying - Activity 1 | WBS-0028 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 153.55 | 76.39 | 77.16 | 28406.75 | 14132.15 | 14970.3572 | 838.2073 | TRUE
TASK-0050 | Zone 05 - Pipe Laying - Activity 1 | WBS-0028 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 81.95 | 44.32 | 37.63 | 11473 | 6204.8 | 6046.271 | -158.529 | TRUE
TASK-0050 | Zone 05 - Pipe Laying - Activity 1 | WBS-0028 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 153.02 | 87.18 | 65.84 | 13006.7 | 7410.3 | 6854.5309 | -555.7691 | TRUE
TASK-0050 | Zone 05 - Pipe Laying - Activity 1 | WBS-0028 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 436.84 | 210.46 | 226.38 | 1834728 | 883932 | 966901.656 | 82969.656 | TRUE
TASK-0051 | Zone 05 - Pipe Laying - Activity 2 | WBS-0028 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 157.1 | 93.61 | 63.49 | 29063.5 | 17317.85 | 16752.2014 | -565.6486 | TRUE
TASK-0051 | Zone 05 - Pipe Laying - Activity 2 | WBS-0028 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 146.41 | 78.18 | 68.23 | 20497.4 | 10945.2 | 11814.7014 | 869.5014 | TRUE
TASK-0051 | Zone 05 - Pipe Laying - Activity 2 | WBS-0028 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 470.98 | 275.33 | 195.65 | 40033.3 | 23403.05 | 23075.1941 | -327.8559 | TRUE
TASK-0051 | Zone 05 - Pipe Laying - Activity 2 | WBS-0028 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 262.7 | 160.04 | 102.66 | 1103340 | 672168 | 635965.176 | -36202.824 | TRUE
TASK-0052 | Zone 05 - Backfill - Activity 1 | WBS-0029 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 413.37 | 158.79 | 254.58 | 11574.36 | 4446.12 | 4739.7004 | 293.5804 | TRUE
TASK-0052 | Zone 05 - Backfill - Activity 1 | WBS-0029 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 93.62 | 37.81 | 55.81 | 39320.4 | 15880.2 | 16101.7038 | 221.5038 | TRUE
TASK-0053 | Zone 05 - Backfill - Activity 2 | WBS-0029 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 240.61 | 115.88 | 124.73 | 6737.08 | 3244.64 | 3266.1364 | 21.4964 | TRUE
TASK-0053 | Zone 05 - Backfill - Activity 2 | WBS-0029 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 378.08 | 189.65 | 188.43 | 158793.6 | 79653 | 76983.1373 | -2669.8627 | TRUE
TASK-0054 | Zone 05 - Backfill - Activity 3 | WBS-0029 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 492.87 | 223.97 | 268.9 | 13800.36 | 6271.16 | 6818.7579 | 547.5979 | TRUE
TASK-0054 | Zone 05 - Backfill - Activity 3 | WBS-0029 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 231.18 | 110.55 | 120.63 | 97095.6 | 46431 | 47974.936 | 1543.936 | TRUE
TASK-0055 | Zone 05 - Reinstatement - Activity 1 | WBS-0030 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 437.75 | 165.3 | 272.45 | 41586.25 | 15703.5 | 16534.693 | 831.193 | TRUE
TASK-0056 | Zone 05 - Reinstatement - Activity 2 | WBS-0030 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 135.59 | 58.86 | 76.73 | 12881.05 | 5591.7 | 5649.6285 | 57.9285 | TRUE
TASK-0060 | Zone 06 - Excavation - Activity 1 | WBS-0033 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 239.85 | 47.11 | 192.74 | 8394.75 | 1648.85 | 1725.1211 | 76.2711 | TRUE
TASK-0061 | Zone 06 - Excavation - Activity 2 | WBS-0033 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 162.41 | 56.12 | 106.29 | 5684.35 | 1964.2 | 1811.0339 | -153.1661 | TRUE
TASK-0062 | Zone 06 - Pipe Laying - Activity 1 | WBS-0034 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 249.41 | 30.11 | 219.3 | 46140.85 | 5570.35 | 5195.4597 | -374.8903 | TRUE
TASK-0062 | Zone 06 - Pipe Laying - Activity 1 | WBS-0034 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 297.65 | 30.5 | 267.15 | 41671 | 4270 | 4692.1546 | 422.1546 | TRUE
TASK-0062 | Zone 06 - Pipe Laying - Activity 1 | WBS-0034 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 499.68 | 60.05 | 439.63 | 42472.8 | 5104.25 | 4782.4373 | -321.8127 | TRUE
TASK-0062 | Zone 06 - Pipe Laying - Activity 1 | WBS-0034 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 486.05 | 59.4 | 426.65 | 2041410 | 249480 | 229862.766 | -19617.234 | TRUE
TASK-0063 | Zone 06 - Pipe Laying - Activity 2 | WBS-0034 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 431.91 | 137.94 | 293.97 | 79903.35 | 25518.9 | 27342.9264 | 1824.0264 | TRUE
TASK-0063 | Zone 06 - Pipe Laying - Activity 2 | WBS-0034 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 268.54 | 86.63 | 181.91 | 37595.6 | 12128.2 | 12865.2143 | 737.0143 | TRUE
TASK-0063 | Zone 06 - Pipe Laying - Activity 2 | WBS-0034 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 230.47 | 71.91 | 158.56 | 19589.95 | 6112.35 | 6703.6809 | 591.3309 | TRUE
TASK-0063 | Zone 06 - Pipe Laying - Activity 2 | WBS-0034 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 220.54 | 82.79 | 137.75 | 926268 | 347718 | 316968.9096 | -30749.0904 | TRUE
TASK-0064 | Zone 06 - Backfill - Activity 1 | WBS-0035 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 169.34 | 36.08 | 133.26 | 4741.52 | 1010.24 | 955.8904 | -54.3496 | TRUE
TASK-0064 | Zone 06 - Backfill - Activity 1 | WBS-0035 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 254.75 | 50.57 | 204.18 | 106995 | 21239.4 | 21570.192 | 330.792 | TRUE
TASK-0065 | Zone 06 - Backfill - Activity 2 | WBS-0035 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 480.79 | 172.06 | 308.73 | 13462.12 | 4817.68 | 4383.2663 | -434.4137 | TRUE
TASK-0065 | Zone 06 - Backfill - Activity 2 | WBS-0035 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 300.1 | 101.98 | 198.12 | 126042 | 42831.6 | 41039.2752 | -1792.3248 | TRUE
TASK-0066 | Zone 06 - Reinstatement - Activity 1 | WBS-0036 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 119.66 | 19.09 | 100.57 | 11367.7 | 1813.55 | 1890.4485 | 76.8985 | TRUE
TASK-0067 | Zone 06 - Reinstatement - Activity 2 | WBS-0036 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 485.92 | 84.56 | 401.36 | 46162.4 | 8033.2 | 7907.6191 | -125.5809 | TRUE
TASK-0071 | Zone 07 - Excavation - Activity 1 | WBS-0039 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 293.99 | 5.92 | 288.07 | 10289.65 | 207.2 | 197.5613 | -9.6387 | TRUE
TASK-0072 | Zone 07 - Excavation - Activity 2 | WBS-0039 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 75.72 | 0 | 75.72 | 2650.2 | 0 | 0 | 0 | TRUE
TASK-0073 | Zone 07 - Excavation - Activity 3 | WBS-0039 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 276.28 | 0 | 276.28 | 9669.8 | 0 | 0 | 0 | TRUE
TASK-0074 | Zone 07 - Pipe Laying - Activity 1 | WBS-0040 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 120.84 | 6.44 | 114.4 | 22355.4 | 1191.4 | 1090.9435 | -100.4565 | TRUE
TASK-0074 | Zone 07 - Pipe Laying - Activity 1 | WBS-0040 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 86.05 | 3.94 | 82.11 | 12047 | 551.6 | 587.8936 | 36.2936 | TRUE
TASK-0074 | Zone 07 - Pipe Laying - Activity 1 | WBS-0040 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 317.77 | 16.05 | 301.72 | 27010.45 | 1364.25 | 1318.11 | -46.14 | TRUE
TASK-0074 | Zone 07 - Pipe Laying - Activity 1 | WBS-0040 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 155.84 | 7.03 | 148.81 | 654528 | 29526 | 31940.9664 | 2414.9664 | TRUE
TASK-0075 | Zone 07 - Pipe Laying - Activity 2 | WBS-0040 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 450.63 | 0.38 | 450.25 | 83366.55 | 70.3 | 75.0299 | 4.7299 | TRUE
TASK-0075 | Zone 07 - Pipe Laying - Activity 2 | WBS-0040 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 317.53 | 0.29 | 317.24 | 44454.2 | 40.6 | 40.0088 | -0.59122 | TRUE
TASK-0075 | Zone 07 - Pipe Laying - Activity 2 | WBS-0040 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 238.65 | 0.22 | 238.43 | 20285.25 | 18.7 | 18.2567 | -0.44327 | TRUE
TASK-0075 | Zone 07 - Pipe Laying - Activity 2 | WBS-0040 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 285.25 | 0.28 | 284.97 | 1198050 | 1176 | 1078.245 | -97.755 | TRUE
TASK-0076 | Zone 07 - Backfill - Activity 1 | WBS-0041 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 141.92 | 6.62 | 135.3 | 3973.76 | 185.36 | 177.6271 | -7.7329 | TRUE
TASK-0076 | Zone 07 - Backfill - Activity 1 | WBS-0041 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 157.41 | 6.89 | 150.52 | 66112.2 | 2893.8 | 2955.2153 | 61.4153 | TRUE
TASK-0077 | Zone 07 - Backfill - Activity 2 | WBS-0041 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 352.26 | 1.62 | 350.64 | 9863.28 | 45.36 | 47.3437 | 1.9837 | TRUE
TASK-0077 | Zone 07 - Backfill - Activity 2 | WBS-0041 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 192.28 | 0.97 | 191.31 | 80757.6 | 407.4 | 387.6365 | -19.7635 | TRUE
TASK-0078 | Zone 07 - Reinstatement - Activity 1 | WBS-0042 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 82.64 | 10.96 | 71.68 | 7850.8 | 1041.2 | 1049.652 | 8.452 | TRUE
TASK-0079 | Zone 07 - Reinstatement - Activity 2 | WBS-0042 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 499.3 | 0 | 499.3 | 47433.5 | 0 | 0 | 0 | TRUE
TASK-0082 | Zone 08 - Excavation - Activity 1 | WBS-0045 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 82.97 | 0 | 82.97 | 2903.95 | 0 | 0 | 0 | TRUE
TASK-0083 | Zone 08 - Excavation - Activity 2 | WBS-0045 | RSRC-006 | Mechanical Excavation | MT | m3 | 35 | 169.34 | 0 | 169.34 | 5926.9 | 0 | 0 | 0 | TRUE
TASK-0084 | Zone 08 - Pipe Laying - Activity 1 | WBS-0046 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 446.39 | 0 | 446.39 | 82582.15 | 0 | 0 | 0 | TRUE
TASK-0084 | Zone 08 - Pipe Laying - Activity 1 | WBS-0046 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 216.29 | 0 | 216.29 | 30280.6 | 0 | 0 | 0 | TRUE
TASK-0084 | Zone 08 - Pipe Laying - Activity 1 | WBS-0046 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 425.19 | 0 | 425.19 | 36141.15 | 0 | 0 | 0 | TRUE
TASK-0084 | Zone 08 - Pipe Laying - Activity 1 | WBS-0046 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 325.25 | 0 | 325.25 | 1366050 | 0 | 0 | 0 | TRUE
TASK-0085 | Zone 08 - Pipe Laying - Activity 2 | WBS-0046 | RSRC-001 | HDPE Pipe 315mm | MT | m | 185 | 344.29 | 0 | 344.29 | 63693.65 | 0 | 0 | 0 | TRUE
TASK-0085 | Zone 08 - Pipe Laying - Activity 2 | WBS-0046 | RSRC-002 | HDPE Pipe 250mm | MT | m | 140 | 417.7 | 0 | 417.7 | 58478 | 0 | 0 | 0 | TRUE
TASK-0085 | Zone 08 - Pipe Laying - Activity 2 | WBS-0046 | RSRC-003 | HDPE Pipe 160mm | MT | m | 85 | 348.52 | 0 | 348.52 | 29624.2 | 0 | 0 | 0 | TRUE
TASK-0085 | Zone 08 - Pipe Laying - Activity 2 | WBS-0046 | RSRC-008 | Gate Valve DN300 | MT | EA | 4200 | 110.43 | 0 | 110.43 | 463806 | 0 | 0 | 0 | TRUE
TASK-0086 | Zone 08 - Backfill - Activity 1 | WBS-0047 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 98.17 | 0 | 98.17 | 2748.76 | 0 | 0 | 0 | TRUE
TASK-0086 | Zone 08 - Backfill - Activity 1 | WBS-0047 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 172.56 | 0 | 172.56 | 72475.2 | 0 | 0 | 0 | TRUE
TASK-0087 | Zone 08 - Backfill - Activity 2 | WBS-0047 | RSRC-005 | Sand Bedding | MT | m3 | 28 | 372.93 | 0 | 372.93 | 10442.04 | 0 | 0 | 0 | TRUE
TASK-0087 | Zone 08 - Backfill - Activity 2 | WBS-0047 | RSRC-004 | Concrete C25 | MT | m3 | 420 | 335.41 | 0 | 335.41 | 140872.2 | 0 | 0 | 0 | TRUE
TASK-0088 | Zone 08 - Reinstatement - Activity 1 | WBS-0048 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 269.84 | 0 | 269.84 | 25634.8 | 0 | 0 | 0 | TRUE
TASK-0089 | Zone 08 - Reinstatement - Activity 2 | WBS-0048 | RSRC-007 | Asphalt Reinstatement | MT | m2 | 95 | 430.75 | 0 | 430.75 | 40921.25 | 0 | 0 | 0 | TRUE

## Project_Info
project_id | project_name | data_date | planned_start | planned_finish | total_activities | completed_activities | inprogress_activities | overall_planned_pct | overall_actual_pct | overall_variance_pct | BAC | PV | EV | AC | SPI | CPI | EAC | VAC
PROJ-001 | Al-Narjis Water Network - Phase 2 | 2026-04-01 | 2024-10-01 | 2026-04-01 | 91 | 15 | 63 | 100 | 52.44 | -47.56 | 25327328.12 | 25327328.12 | 13458234.63 | 13388663.04 | 0.5314 | 1.0052 | 25196399.91 | 130928.21

## SCurve
period_date | planned_cum_pct | actual_cum_pct | planned_cum_cost | actual_cum_cost
2024-10-01 | 0.05 | 0.01 | 12121.85 | 1801.71
2024-11-01 | 0.13 | 0.18 | 32690.62 | 23551.13
2024-12-01 | 0.29 | 0.33 | 72884.93 | 44110.74
2025-01-01 | 1.02 | 0.72 | 259407.87 | 96288.17
2025-02-01 | 7.5 | 7.58 | 1898891.06 | 1014205.26
2025-03-01 | 28.22 | 29.61 | 7147253.89 | 3964061.97
2025-04-01 | 55.94 | 44.08 | 14168117.78 | 5901995.35
2025-05-01 | 82.63 | 85.74 | 20927407.86 | 11479715.39
2025-06-01 | 91.43 | 91.81 | 23155726.95 | 12292763.98
2025-07-01 | 94.44 | 94.31 | 23918769.44 | 12626950.59
2025-08-01 | 97.2 | 98.05 | 24617236.89 | 13127842.8
2025-09-01 | 98.51 | 98.57 | 24950547.96 | 13197372.57
2025-10-01 | 99.03 | 99.28 | 25081291.14 | 13291653.14
2025-11-01 | 99.64 | 99.64 | 25235220.4 | 13340206.76
2025-12-01 | 100 | 100 | 25327328.12 | 13388663.04
2026-01-01 | 100 | 100 | 25327328.12 | 13388663.04
2026-02-01 | 100 | 100 | 25327328.12 | 13388663.04
2026-03-01 | 100 | 100 | 25327328.12 | 13388663.04